AURELIAN GLOBAL HOLDINGS PLC

Group Procurement — Technology Services

REQUEST FOR PROPOSAL

Data Centre Exit and Hosted Compute Services

| Field | Detail |
| --- | --- |
| RFP reference | AG/2026/IAAS/402 |
| Issue date | 11 August 2026 |
| Clarification deadline | 1 September 2026 |
| Response deadline | 25 September 2026, 17:00 CET |
| Contract commencement | 1 April 2027 |
| Issuing entity | Aurelian Global Holdings plc |

1.  Introduction

Aurelian Global Holdings plc operates two owned data centres in the United Kingdom and Germany. The lease on the German facility expires in September 2028 and will not be renewed; the UK facility requires significant mechanical and electrical investment to remain viable beyond 2029.

The Board has approved an exit from both facilities and the migration of all workloads to hosted infrastructure.

2.  Scope of services

Assessment and migration planning for the workloads listed in Annex A.

Design and build of the target hosting environment.

Migration, testing and cutover of all in-scope workloads.

Provision of compute, storage and network capacity for the term.

Backup and recovery services.

Decommissioning support for the vacated facilities.

Application remediation and any re-platforming beyond a like-for-like migration are out of scope and will be handled by Aurelian's application teams.

3.  The estate

The current estate is set out in Annex A, which is the authoritative statement for pricing purposes. Approximate figures elsewhere in this document are indicative.

The estate comprises roughly five hundred and fifty virtual machines supporting around two hundred distinct workloads. Non-production environments represent approximately 60% of the production footprint and are not required outside working hours.

Storage is tiered across performance, standard and archive classes. Monthly outbound data transfer averages 42 TB.

4.  Service requirements

| Ref | Requirement | Target |
| --- | --- | --- |
| IA-01 | Platform availability | 99.9% |
| IA-02 | Recovery time objective — tier 1 workloads | 4 hours |
| IA-03 | Recovery point objective — tier 1 workloads | 1 hour |
| IA-04 | Backup retention | See note |
| IA-05 | Capacity reporting | Monthly |
| IA-06 | Security patching of the hosting platform | Within vendor guidance |

Note on IA-04: Aurelian's records-retention policy is under review following a regulatory change in the German business. Suppliers should price a stated retention period and show the incremental cost of longer alternatives.

Aurelian has stated an availability target but has not specified the resilience architecture required to achieve it. Suppliers should set out what their proposal assumes.

5.  Programme

The German facility must be vacated by 30 September 2028. The UK facility should follow within a further twelve months.

Aurelian's application teams have limited capacity to support concurrent migration activity, and the Group's change freeze runs from mid-November to early January each year. Suppliers should propose a migration profile consistent with these constraints and state the assumptions on which their consumption forecast is based.

6.  Commercial requirements

The contract will be awarded for an initial term of 5 years.

Pricing shall separate one-off migration charges from recurring consumption. Suppliers should state clearly the basis on which consumption is charged and how it varies across the term.

Aurelian is willing to consider capacity commitments in exchange for reduced unit rates but has taken no decision. Suppliers should present the options available and the trade-off each involves.

Aurelian's platform operations team will be retained in some form. The division of operational responsibility between that team and the supplier has not been determined.

Annex A  —  Infrastructure inventory

The following is the authoritative statement of the estate in scope.

| Class | Specification | Production | Non-production | Total |
| --- | --- | --- | --- | --- |
| Small | 2 vCPU / 8 GB | 150 | 90 | 240 |
| Medium | 4 vCPU / 16 GB | 113 | 67 | 180 |
| Large | 8 vCPU / 32 GB | 59 | 36 | 95 |
| XLarge | 16 vCPU / 64 GB | 18 | 10 | 28 |
| GPU | 8 vCPU / 61 GB + GPU | 6 | 0 | 6 |
| Total |  | 346 | 203 | 549 |

Storage: 180 TB performance, 640 TB standard, 2,100 TB archive.

Outbound data transfer: 42 TB per month averaged over the last 12 months.

Distinct workloads in scope: 210.

Note: the non-production column is included in the totals above and is not required outside working hours.